## ADNSA Actions
ADNSA-ACTIONS/DECISIONS
Item | Mtng Date: | Action required: | By: | Due date: | Status: | Decision | Effective
6 | 2013-09-30 | Jasmine to release documentation regarding student suggestions for future visiting speakers | Jasmine | 2015-05-04 | Ongoing | Mar 16/15: will raise the topic w Julia.
2 | 2013-10-21 | Nicole, Ellen, Sarah to provide names of students who attended past NPLEX review courses to Jasmine | Nicole, Ellen, Sarah | 2013-10-28 | Ongoing | Nicole will re-send email next semester
1 | 2013-11-11 | Shehab and Jasmine to consider Yr 1 Physiology course change suggestions | Shehab, Jasmine | 2015-09-01 | In progress | Mar 16/15 will be accountable to present something on this in the Town Hall in Sept 2015.
3 | 2014-06-09 | Shehab to investigate Biochemistry delivery and report back to ADNSA | Shehab | 2014-11-10 | ON HOLD | Deprioritized - review in the summer
1 | 2014-06-16 | Jasmine to set up a focus group regarding Ndnet use and needs by students, faculty and administration | Jasmine | 2014-10-13 | ON HOLD | SEPT 29, 2014 on hold, pending the new CCO
1 | 2014-07-28 | Shehab to put together proposal for online based Men's and Women's Health summer class | Shehab | 2014-10-13 | Re-activated Nov 24/14 | request from students was to videotape lectures for these students
2 | 2014-07-28 | Shehab to re-examine Men's and Women's Health 2 (Yr4) curriculum for potential overlap with other classes; Re-assigned to JC on Nov 24/14 | Jasmine | 2015-09-01 | Mar 16/15 will present something in Sept 2015.
3 | 2014-07-28 | Nicole to discuss concerns with Men's and Women's Health research assignment with Dr. Uraz and report back | Shehab | 2015-03-23 | Reactivated Nov 24/14 | Mar 16/15 Shehab will ask for a report back from Nicole.
3 | 2014-10-06 | look to NSA to provide an alternative for class reps in terms of dealing with advertisements/marketing posts | VP Academics, Cindy, Patti | 2015-09-00 | In progress | APR 13/15 will report back in summer; item is pending Patti to further discuss issue --> Cindy will send Patti a gentle reminder | JAN 12/15: Dave to provide update next wk
2 | 2014-10-20 | contact IS department (Paul Battistuzzi) as to current status on WIFI connectivity and plans for improvements in summer | Cindy | 2015-09-00 | In progress | APR 13/15: CINDY will f/u w IS dept.
3 | 2014-10-20 | speak with Michael re: library hours on Sundays --> Jan Intake are not getting Sunday hours | Jasmine | 2015-05-11 | In progress | APR 13/15: will f/u w Michael to find out why Jan intake aren't getting their Sunday hours --> will also look at year-at-a-glance once it's released
4 | 2014-10-20 | meet with a select group of students (post-ACF) re: potential changes to exam scheduling | SE-H, VP Academics | 2015-05-25 | In progress | APR 13/15: will discuss this issue over the summer
5 | 2014-11-10 | draw up student advocate guide re: duties, info of appeals process, and on appeals themselves | Dave, Carleigh, Ellen | 2015-05-11 | In progress | APR 13/15 Jasmine will f/u w Dave re: guide for students --> will work on throughout summer
1 | 2015-01-12 | compile a document outlining the selection criteria for clinic focus shifts for subsequent years | Mitchell | 00-Oct-15 | In progress
2 | 2015-01-12 | work on finding out the time-lines for grade-releases, and whether there’s a more efficient way for this process to occur | Shehab, Melanie | 00-Sep-15 | In progress | APR 13/15 Melanie will look into this and report back
1 | 2015-01-19 | develop a better set of standards re: course notes and examinations. Goal: work with faculty and figure what is reasonable [i.e. when, what, and the quality] | Shehab | 00-Sep-15 | In progress | APR 13/15 Shehab will put together a focus group with faculty (summer project)
2 | 2015-01-19 | will put together a sub-group involving students and faculty reps and admin to discuss how to maintain integrity b/w exams | JC | 2015-02-03 | In progress | JAN 19/15 will take feedback and itemize what the issues are
1 | 2015-01-26 | info re: NPLEX results to be disseminated to students | Shehab | 2015-03-31 | In progress
2 | 2015-01-26 | the issue re: adjusting exam marks must be brought to the attention of NSA to clarify what is, and what is not, done with exams --> students can be better informed about the process | Shehab | 2015-03-31 | In progress
3 | 2015-01-26 | issue re: exam scheduling --> want to stress to students what re-scheduling an exam really entails | Shehab | 2015-03-31 | In progress
4 | 2015-01-26 | take the following issue to ACC: shifting a 4th yr course's mid-term to early March to accommodate students attending externships and scheduling a class session during the Feb mid-term week | Jasmine, Shehab | 2015-03-31 | In progress
5 | 2015-01-26 | Advanced Standing: develop a strategy to ensure rubrics are clear and available for students, and also look at what communication is currently in place | Jasmine, David | 2015-03-31 | In progress
1 | 2015-02-09 | Switch Clin Phys II bell-ringer to last lab session and written final to bell-ringer slot in exam schedule | Shehab, Melanie | 2015-03-16 | In progress | MAR 9/15: MK will make those changes once she confirms with the prof.
1 | 2015-03-09 | 3rd yr BOT MED exam: will see what Dr. Barlow thinks about extending the exam time | Jasmine, Shehab, MK | ASAP | In progress | APR 13/15 Melanie will F/U w Dr. Barlow as to whether BOT 302 exam has been extended
2 | 2015-03-09 | continue to work with faculty: develop set of guidelines for exam writing, how to effectively write an exam and budget time --> ultimately help students prepare for NPLEX | Jasmine, Shehab | Ongoing | In progress
3 | 2015-03-09 | communications to present to students showing college's effort in trying to negotiate loan limits with financial institutions --> will put together a report to share with this group and review what could be published and presented to students | Dave, Patti | 2015-04-13 | In progress
4 | 2015-03-09 | Anatomy Mid-term: dropped questions --> will prepare a statement explaining what transpired and send it to Shreya likely by tomorrow | Cindy | 2015-03-16 | In progress
5 | 2015-03-09 | Extended library hours for Jan intake: will contact Michael and find out feedback upon the implementation of extended hours and then report back | Dave | 2015-03-16 | In progress
1 | 2015-03-16 | PCD: meeting with 2nd year reps, Gyne coordinator: Dr. Kate Whimster, and Dr. P. to discuss general inconsistencies and disorganization of the instructions provided, including expectations of the students | SE-H, 2nd Yr Reps, Kate Whimster, Dr. Pachkovskaja | 2015-04-20 | In progress
1 | 2015-03-23 | ACUPUNCTURE DROP-IN SESSIONS: Year 2 class reps must ask students which day works better for the drop-in session and report back to MK | 2nd Yr Reps, MK | 2015-03-30 | In progress
2 | 2015-03-23 | Student business cards: DH and Patti will contact Marketing Department on status of the cards and report back | Dave | 2015-03-30 | In progress
3 | 2015-03-23 | Student Surveys: everyone will brainstorm and report back with ideas as to what kind of incentives can be implemented to promote class participation | Deans, CB, MK, Reps | 2015-03-30 | In progress
4 | 2015-03-23 | information on NPLEX prep courses: will speak w Ellen and see if she would be willing to put something together or find out how they did it last year | Jasmine | 2015-03-30 | In progress
5 | 2015-03-23 | information on NPLEX prep courses: will look up the deadlines for each course and see if there’s any flexibility with the NPLEX dates | Sarah | 2015-03-30 | In progress
6 | 2015-03-23 | Anonymous Px feedback forms: will look into implementing these forms and also having them part as a formative assessment tool for learning purposes | Mitchell | 2015-03-30 | In progress
1 | 2015-03-30 | Compile a report around QA and QC re: exam prep to exam scoring - a commitment has been made for a preliminary report to be prepared for the January class | CB, NDG, SE-H | 2015-09-01 | In progress
1 | 2015-04-13 | Cindy will f/u with Michael regarding the issue of out-dated printers in library | CB | 2015-05-11 | In progress
2 | 2015-04-13 | Pediatrics Final: will look into open-book allows for laptop use during exam | MK | ASAP | In progress
3 | 2015-04-13 | Jasmine to speak to Shehab re: outstanding assignment grades for IMG cohort | JC | ASAP | In progress | APR 13/15 plans to include direction in faculty handbook
4 | 2015-04-13 | Rick will f/u with Dr. Zeifman as to when to book vacation during clinic | RB | 2015-05-11 | In progress
5 | 2015-04-13 | Jasmine to provide direction in faculty handbook re: posting lecture note revisions | JC | 2015-05-11 | In progress
2 | 2015-05-11 | Cindy to f/u with Mitchell re: problematic interactions with patient and intern, how to report | CB | 2015-06-01
3 | 2015-05-11 | Cindy to f/u with Mitchell re: method of switching interns, current process is awkward as having to confront the itnern | CB | 2015-06-01
1 | 2015-05-28 | DH to f/u with Michael re status of chairs being replaced in the LRC | DH | 2015-06-01
2 | 2015-05-28 | Shehab to report back following EC re status of test centre & details | S.EH | 2015-06-04
3 | 2015-05-28 | Shehab and Melanie to develop timeline re release of Year at a Glance & Exam Schedules for 2015/2016 | S.EH & MK | 2015-08-01
no meeting - June 4, SCC week
1 | 2014-06-25 | Cindy to ask Jasmine if there is a grade cut off requirement for residency. | C.B.
no meeting - July 9, SCC week
1 | 2015-07-16 | Cindy to follow up with Shehab re: if student can alternate partners in practicals to gain exposure to different bodies | C.B. | 2015-07-23
1 | 2015-07-16 | Cindy to follow up with Shehab re: students concern with Fall Monday classes, will only have 11 weeks of delivery | C.B. | 2015-07-23 |  | Shehab addressed at July 23 ADNSA; will review with faculty on how delivery will handled
1 | 2015-07-23 | Shehab to address with faculty delivery of Monday fall classes to ensure essential materials covered in 11 week delivery | S.E.H. | Fall 2015
2 | 2015-07-23 | Timing of step 3 review is difficult for students to attend, often during class time. Shehab will review with faculty for suggestions re: preassigned times | S.E.H. | mid Sept 2015
| no meeting - July 9, SCC week | October 5-19 b/c of SCC, Thanksgiving, and Exam week
1 | 2015-10-26 | Cindy will put together and draft a version re: TA and student conflict resolution steps (will create a flow-chart) | Cindy B. | Nov 9 2015
1 | 2015-11-09 | Shehab will send something out re: uploading class notes in a timely manner; will check when notes are uploaded on moodle for the 3rd year courses --> f/u nxt week | SE-H | Nov 16 2015
1 | 2015-11-16 | Cindy will formulate a standard text for class reps to forward to vendor reps | Cindy B. | Nov 23 2015
2 | 2015-11-16 | Cindy will talk with Keith about the legalities around class audio recordings and report back to the group next week | Cindy B. | Nov 23 2015
1 | 2015-11-23 | MZ: Will send an e-mail off to Dr. Khalili --> will look for possible solutions to issue of shadowing students not being able access PAX to check for changes to shifts --> check back in 2 weeks | M.Z. | Dec 14 2015
1 | 2015-12-07 | Jasmine: will put together a summary from ADNSA MMs --> have it reviewed and post it for following week --> can be the verbal commentary reps can work with when providing info to students | J. C. | Jan 11 2016
1 | 2016-01-18 | Jasmine & Parmie: will create a template of FAQs that have been brought up throughout ADNSA meetings | J. C. & Parmie | TBD
2 | 2016-01-18 | S-EH will look into the issue of missing or incorrect exam marks on moodle | S-EH | TBD | Completed | First episode operator mistake - not a pattern, no additional action at this time; second episode was a question frameshift on an accomodation exam. Considering a checklist for formating accomodation exams going forward.
1 | 2016-01-25 | Approval of the minutes to a more concise format (Postponed) | ALL | 2016-03-21
2 | 2016-01-25 | Dr. S-EH to develop a paragraph explaining rationale for instructors not being present for exams | S-EH | TBD
3 | 2016-01-25 | Active monitoring of BAS119 progress and report to ADNSA post-midterms | S-EH, GN | TBD
4 | 2016-01-25 | Dr. S-EH to create a report comparing reported grade errors in past and current year to illustrate improvements and address concerns | S-EH | TBD
5 | 2016-01-25 | Dr. S-EH to send out an email to instructors for feedback around random group assignment and MC to meet with two instructors to discuss group formation | S-EH & MC | Feb 8 2016
1 | 2016-03-12 | OL to send Dr. JC an email with information about TedTalks at CCNM to be directed to the marketing department | OL & Dr. JC | TBD
2 | 2016-03-12 | MK and Dr. S-EH to develop a system of proofreading exams to ensure accuracy | MK & Dr. S-EH | 2016-03-21
3 | 2016-03-12 | Dr, JC to survey faculty to determine typical response to exam comments on back of scantron sheets | Dr. JC | 2016-03-21
4 | 2016-03-12 | Dr, JC to investigate anti-oppression training and possible ways to integrate into CCNM curriculum | Dr. JC | TBD

## COMPLETED Actions
ADNSA-ACTIONS/DECISIONS
Item | Mtng Date: | Action required: | By: | Due date: | Status: | Decision | Effective
1 | 2013-09-16 | Lawrence to email Shehab and Jasmine regarding internet access improvement | Lawrence | 2013-09-30 | Completed
2 | 2013-09-16 | ADNSA members to return textbook feedback to Jasmine | All Reps | 2013-09-23 | Completed | Returned to Mitchell Sep 23
3 | 2013-09-16 | Shehab to look into switching Yr 3 Homeopathy classroom from MPR to Lecture Theatre | Shehab | 2013-09-23 | Completed | Not possible at this time due to scheduling conflicts
4 | 2013-09-16 | Jasmine to speak with Dr. Saranchuk regarding extension of weekend library hours | Jasmine | 2013-09-23 | Completed | See Sept 23, 2013 Actions below
5 | 2013-09-16 | Jasmine to look into moving Yr 2 Clinical Medicine Midterm Exam later (11am/noon) | Jasmine | 2013-09-23 | Completed | Exam is now Oct 18, 11am
6 | 2013-09-16 | Shehab to look into moving IMG final exams earlier in the day at end of exam week | Shehab | 2013-09-23 | Completed | Bot Med 202i midterm is now Oct 17 2:30pm, Bot Med 202i final exam is now Dec 13, Pediatrics final exam is now Dec 12
7 | 2013-09-16 | Jasmine will speak with Rob to have him attend next ADNSA meeting regarding temperature of Classroom 4 | Jasmine | 2013-09-23 | Completed | Rob to attend ADNSA meeting Oct 7
8 | 2013-09-16 | Jasmine will speak with property staff and regarding cost of replacing desks in Classroom 4 | Jasmine | 2013-09-23 | Completed | Possibility explored at Admin Meeting, Rob says unlikely to renovate like lecture theatre due to capacity requirements
9 | 2013-09-16 | Jasmine will present findings of Intern Counseling survey to Depatmental Meeting | Jasmine | 2013-09-23 | Completed | Findings presented
10 | 2013-09-16 | Tara to remind clinic staff of intern breastfeeding policy | Tara | 2013-09-23 | Completed | Memo sent to all clinic staff and supervisors regarding policy
11 | 2013-09-16 | Patti to investigate availability of child care/breastfeeding area for intern use | Patti | 2013-09-23 | Completed | See Sept 23, 2013 Actions below
12 | 2013-09-16 | Mitchell will post Preceptorship Requirements for Class of 2015 and to look into meetings with classes to clarify requirements | Mitchell | 2013-09-23 | Completed | Meeting booked with Yr 3 Class Tues Oct 1 11:30 Lecture Theatre to address issues
13 | 2013-09-16 | Mitchell to investigate an automatic alert when students submit preceptorship hour sheets to the Office of Clinical Education | Mitchell | 2013-09-23 | Completed
1 | 2013-09-23 | Shehab to finalize exam schedule | Shehab | 2013-10-07 | Completed
2 | 2013-09-23 | Mitchell to speak to Dr. Saranchuk regarding Library hours: Sat 9-5, Sundays in month before final exams | Mitchell | 2013-09-30 | Completed | See Sept 30, 2013 Actions below, Action 1
3 | 2013-09-23 | Mitchell to report on how Health Psychology course notes to be released to 4th year interns | Mitchell | 2013-10-28 | Moved to Oct 21
4 | 2013-09-23 | Patti to report back on progress of child friendly/breast feeding space | Patti | n/a | Completed
5 | 2013-09-23 | Shehab to look into scheduling of acupuncture drop-in sessions | Shehab | 2013-10-07 | Completed | See Oct 21 2013 Actions below; transferred to Melanie
6 | 2013-09-23 | Shehab to consult IMG reps when curriculum reviewed for next IMG class | Shehab | n/a | Completed
7 | 2013-09-23 | Shehab to organize meeting for PCD/Primary Care discussion with Dr. Roberts/Gilbert/Yr2,3,4 reps | Shehab | 2013-09-30 | Completed
8 | 2013-09-23 | Ashley, Nicole, Christine to formulate list of TA concerns regarding PCD/Primary Care | Ashley, Nicole, Christine | 2013-09-30 | Completed | Ashley met with Dr. Pachkovskaja regarding concerns, email sent to class regarding expectations, positive feedback received
1 | 2013-09-30 | Jasmine to speak with Dr. Saranchuk to attend Oct 7 ADNSA meeting | Jasmine | 2013-10-07 | Completed
2 | 30=Sep-13 | Shehab/Melanie to release final exam schedule to Moodle Oct 24 | Shehab, Melanie | 2013-10-07 | Completed
3 | 2013-09-30 | Jasmine to forward internet updates to IS | Jasmine | 2013-10-07 | Completed
4 | 2013-09-30 | Cynthia to conduct focus groups for Yr 2 Oct 23 | Cynthia | 2013-10-23 | Completed
5 | 2013-09-30 | Rana to submit letter of IMG concerns to Dr. El-Hashemy, Carino and Zeifman | Rana | 2013-10-07 | Completed
1 | 2013-10-07 | Shehab to send memo to Instructors regarding internet usage in class | Shehab | 2013-10-28 | Completed
2 | 2013-10-07 | Shannon to send letter detailing conflict of interest policy to Patti, Patti/Jasmine to look into student rep policy | Shannon, Patti, Jasmine | 2013-10-28 | Completed
1 | 2013-10-21 | Nicole to send email to Yr 3 class to recruit for Cynthia's Focus group Oct 23 | Nicole | 2013-10-23 | Completed
3 | 2013-10-21 | Patti to look into which bursaries IMGs can apply for | Patti | 2013-10-28 | Completed
4 | 2013-10-21 | Jasmine to contact Nicole regarding time for Yr 3 meeting with Deans | Jasmine | 2013-10-28 | Completed
5 | 2013-10-21 | Shehab to discuss Yr 2 acupuncture exam format changes with Dr. Kassam | Shehab | 2013-10-28 | Completed
6 | 2013-10-21 | Melanie to look into scantron informational sheet/video for next exam period | Melanie | 2013-11-04 | Completed
7 | 2013-10-21 | Ashley to forward email attachment that couldn't be forwarded to Patti for investigation | Ashley, Patti | 2013-10-28 | Completed
8 | 2013-10-21 | Ellen, Sarah to set up poll/focus group to assess need for hydro/massage review for Yr 3 | Ellen, Sarah | 2013-11-04 | Completed
9 | 2013-10-21 | Mitchell to report on how Health Psychology course notes to be released to 4th year interns | Mitchell | 2013-10-28 | Completed
1 | 2013-11-25 | Sarah and Ellen to address student email policy with Cynthia in Jan 2014 | Sarah, Ellen, Cynthia | 2014-01-13 | See Jan 13 Actions
2 | 2013-11-25 | Cheryl to send out information to Yr 2 class regarding preceptorship requirements | Cheryl | 2014-01-13 | Completed
1 | 2014-01-13 | Sarah and Ellen to address student email policy with Cynthia in Jan 2014 | Sarah, Ellen, Cynthia | Jan | See Jan 27 Actions
2 | 2014-01-13 | Sarah and Ellen to assess need for hydro/massage review for Yr 3 | Sarah, Ellen | 2014-01-20 | Completed
3 | 2014-01-13 | Melanie to follow up with Dr. Kwok for appropriate dates for acupuncture practice sessions | Melanie, Ellen | 2014-01-20 | See Jan 20 Actions
4 | 2014-01-13 | Melanie to follow up regarding Yr 4 Practice Mgmt/Ethics time switch | Melanie | 2014-01-20 | See Jan 27 Actions
5 | 2014-01-13 | Melanie to look into alternate date for Bot Med 3 exam | Melanie | 2014-01-20 | See jan 27 Actions
6 | 2014-01-13 | Jasmine to release objectives of anti-oppression training on ADNSA Moodle; to be discussed in ADNSA | Jasmine | 2014-01-20 | Completed
7 | 2014-01-13 | Shehab to report back on anatomy, IT1, Bot Med 3 grading (slow release) | Shehab | 2014-01-20 | Completed
8 | 2014-01-13 | Shehab to release proposed changes to incorporate burnout prevention into program; to be discussed in ADNSA | Shehab | 2014-01-20 | See Jan 31 Actions
9 | 2014-01-13 | Shehab to look into Physical Medicine Ankle exam issue; Nicole to forward complaint to Shehab | Shehab, Nicole | 2014-01-20 | Completed
10 | 2014-01-13 | Mitchell to look into dates for CLE201 shifts | Mitchell | 2014-01-20 | See Jan 20 Actions
11 | 2014-01-13 | Mitchell to contact specialty shift supervisors regarding selection | Mitchell | 2014-01-20 | Completed
12 | 2014-01-13 | Mitchell to look into updating preceptorship list | Mitchell | 2014-01-20 | Completed
13 | 2014-01-13 | Hany/Rana to report back regarding any additional email problems with IMG class | Hany, Rana | 2014-01-20 | Completed
1 | 2014-01-20 | Shehab to speak to Melanie regarding OSCE makeup scheduling and cost for PCD makeup | Shehab | 2014-01-27 | Completed
2 | 2014-01-20 | Shehab to look into addition of Physiology midterm time to schedule on Moodle | Shehab | 2014-01-27 | Completed
2 | 2014-01-20 | Mitchell to organize sending out incomplete hours/contacts for CLE201 by student number | Mitchell | 2014-01-27 | Completed
3 | 2014-01-20 | Mitchell to look into posting of make-up sign up sheet for missed shifts in CLE201 (with Dr. Khalili and Diana) | Mitchell | 2014-01-27 | Completed
4 | 2014-01-20 | Mitchell to send out email to Yr 3 class regarding Q&A for shift selection; tentatively 2nd week Feb | Mitchell | 2014-01-27 | Completed
5 | 2014-01-20 | Shehab/Jasmine to bring up tutor allowance for PCD, Point Location, Motion Palpation at Curriculum Committee | Shehab, Jasmine | 2014-01-27 | Completed
6 | 2014-01-20 | Shehab/Jasmine to bring up hydro/massage review session to Curriculum Committee | Shehab, Jasmine | 2014-01-27 | See Jan 31 Actions
7 | 2014-01-20 | Ellen to email Melanie for dates of acupuncture practice sessions | Ellen | 2014-01-27 | Completed
1 | 2014-01-27 | Melanie to follow up regarding Yr 4 Practice Mgmt/Ethics time switch | Melanie | 2014-01-20 | See Feb 10 Actions
2 | 2014-01-27 | Melanie to look into alternate date for Bot Med 3 exam | Melanie | 2014-01-20 | See Feb 10 Actions
3 | 2014-01-27 | Patti to look into establishment of Communications Committee (re: student emails) | Patti | 2014-02-10 | Completed
4 | 2014-01-27 | Patti to speak to IS regarding Moodle crashing on Saturdays | Patti | 2014-02-10 | Completed
5 | 2014-01-27 | Ellen to report back with dates for hydro/massage review and acupuncture practice sessions | Ellen | 2014-02-10 | Completed
6 | 2014-01-27 | Cynthia to report on Academic Burnout prevention strategies | Cynthia | 2014-02-28 | See Feb 10 Actions
1 | 2014-02-10 | Melanie to follow up regarding Yr 4 Practice Mgmt/Ethics time switch | Melanie | 2014-01-20 | Completed
2 | 2014-02-10 | Nicole to send email to Melanie regarding rescheduling of Bot Med 3 final exam | Nicole | 2014-02-17 | Completed
3 | 2014-02-10 | Melanie to establish midterm time for Sept Yr 1 Physiology bellringer | Melanie | 2014-02-17 | See Mar 10 Actions
4 | 2014-02-10 | Cynthia to add coping skills survey to course evaluation surveys | Cynthia | 2014-02-17 | Completed
5 | 2014-02-10 | Patti/Cynthia to put out school-wide email to promote completion of surveys | Patti, Cynthia | 2014-02-17 | Completed
6 | 2014-02-10 | Nicole to send email to Melanie/Patti to make Yr 3 Bot Med exam review available | Nicole | 2014-03-10 | Completed
7 | 2014-02-10 | Patti/Tara/Ellen to report back on communications committee proceedings | Patti, Tara, Ellen | 2014-03-10 | See Mar 10 Actions
8 | 2014-02-10 | Patti/Shehab to inform ADNSA of timeline for tutor availability for practical courses | Patti, Shehab | 2014-03-10 | Completed
9 | 2014-02-10 | Sheldon to report on physiology course feedback from Sept Yr 1 class | Sheldon | 2014-03-10 | See Mar 10 Actions
10 | 2014-02-10 | Shehab to speak to Dr. Fraser about Biochemistry concerns of Jan Yr 1 class | Shehab | 2014-03-10 | Completed
11 | 2014-02-10 | Shehab to report back on hydrotherapy review session time | Shehab | 2014-03-10 | Completed
12 | 2014-02-10 | Cindy to update ADNSA regarding coping skills survey result | Cynthia | 2014-04-07 | Completed
1 | 2014-03-10 | Melanie to establish time for Sept Yr 1 Physiology bellringer | Melanie | 2014-03-24 | Completed
2 | 2014-03-10 | Patti to report back on communications committee proceedings | Patti | 2014-03-17 | Completed
3 | 2014-03-10 | Sheldon to report on physiology course feedback from Sept Yr 1 class | Sheldon | 2014-04-07 | Completed
4 | 2014-03-10 | Shehab to report regarding statistics of Jan Yr 1 Biochemistry background and academic performance | Shehab | 2014-04-07 | Completed
1 | 2014-03-17 | Nicole to report back on clinic orientation needs from Yr 3 | Nicole | 2014-04-07 | Completed
1 | 2014-03-24 | Shehab and Jasmine to speak to Dr. Kassam regarding potential for Asian Med theory drop-in session | Shehab, Jasmine | 2014-04-07 | Completed
2 | 2014-03-24 | Shehab to look into reason for Yr 2 Pharmacology midterm time change without class approval | Shehab | 2014-04-07 | Completed
3 | 2014-03-24 | Sheldon to report on potential for Dr. Terzic to teach Yr 1 Physiology | Sheldon | 2014-04-07 | Completed
4 | 2014-03-24 | Melanie to release official notice regarding Yr 1 Physiology exam time | Melanie | 2014-04-07 | Completed
1 | 2014-04-14 | Sheldon to forward Yr 1 Physiology comments/Dr. Terzic comments to Cindy | Sheldon | 2014-04-21 | Completed
1 | 2014-05-26 | Laura to discuss idea of Pass/Fail system in Yr 1 and 2 with the NSA and report back | Laura | 2014-09-15 | Completed
2 | 2014-05-26 | Cindy to speak to Dr. Lander about scheduling conflict of Clinical Nutrition with Dr. Godfrey memorial | Cindy | 2014-06-04 | Completed
1 | 2014-06-09 | Shehab to investigate request to move June 30 Physiology Lab to July 2 | Shehab | 2014-06-16 | Completed
2 | 2014-06-09 | Laura to put forward formal NSA proposal to investigate Pass/Fail as grading system at CCNM | Laura | 2014-09-22 | Completed | proposal with a submission was put forward on Sept 22, 2014
2 | 2014-06-16 | Shehab to send memo to Yr 1 Jan students regarding June 30 Physiology lab decision | Shehab | 2014-06-23 | Completed
1 | 2014-07-14 | Keep on ADNSA agenda, request for NSA support for IMG Class Rep, only Rick has been active in the role, the 2nd class rep. has not been participating. | NSA | 2014-07-21 | Completed | IMG Bot Med class time overlapped with ADNSA meeting time - In September this will not present a problem and will be taken into account next summer (12:30 start time of ADNSA meeting)
2 | 2014-07-14 | Shehab to present update on Physiology project | Shehab | 2014-07-21 | Completed
1 | 2014-07-21 | Dave Hall to organize joint meeting between Acadmics and Student Services to discuss registration issues | Dave | 2014-07-28 | Completed
2 | 2014-07-21 | Shehab to present future design of physiology courses to ADNSA | Shehab | 2014-08-11 | Completed | information posted on ADNSA
4 | 2014-07-28 | Sarah to bring up concerns regarding Physiology TA lab preparation to course instructor and report back | Sarah | 2014-08-11 | Completed
1 | 2014-09-22 | Sheryl instructed by SE-H to write a proposal RE: 2 exams on Friday for further consideration. | Sheryl | 2014-09-29 | Completed
2 | 2014-09-22 | Jasmine to speak with Keith Pownell RE: regulatory information and incorporating it into overall program | Jasmine | 2014-10-06 | Completed | currently informed not enough is being done in Ethics & Jurisprudence courses --> will look at where is the best fit --> ensure it's part of the overall program
3 | 2014-09-22 | Mitchell to contact CONO: facilitate information sent directly to students or representatives | Mitchell | 2014-10-06 | COMPLETED | JAN 12/15: will put it in hands of NSA to act as communication b/w CONO and student body as a whole
5 | 2014-09-22 | Rick instructed to send an e-mail to discuss issue of 2 final exams in one day during midterm week | Rick | 2014-10-06 | Completed
6 | 2014-09-22 | Sarah will speak with Dr. Terzic RE: Anatomy Cadaver Lab and report back | Sarah | 2014-09-29 | Completed
2 | 2014-09-29 | Shehab to look into the possibility of shifting over midterm exam for either Phys Med or Women's Health | Shehab | 2014-10-06 | Completed
3 | 2014-09-29 | Jasmine to send class representatives information regarding MSK focus group participation | Jasmine | 2014-10-06 | Completed | sent e-mail to class reps re: MSK focus groups
5 | 2014-09-29 | Shehab will communicate with the OAA about posting the exact times for exams on the schedule | Shehab, Melanie | 2014-10-20 | COMPLETED | JAN 12/15: SE-H & MK currently working on this and will see this fully implemented for next exam cycle SEPT '15
1 | 2014-10-06 | Shehab and Melanie to communicate with faculty re: 3 day class note posting rule on moodle | Shehab, Melanie | 2014-10-27 | AMALGAMATED W ITEM #2 | SE-H to send class reps an excel chart to fill out
1 | 2014-11-10 | will speak with Dr. Roberts re: missed Clin Med I classes and report back | Shehab | 2014-11-17 | Completed
2 | 2014-11-10 | will look at final exam sched for IMG re: switching homeopathy and botanicals | Melanie | 2014-11-17 | Completed
4 | 2014-11-10 | will put together a package for appeals document outlining the process | Dave, Carleigh | 2015-01-01 | AMALGAMATED W ITEM #5
1 | 2014-09-29 | Shehab to communicate with Dr. Terzic RE: Anatomy Cadaver Labs and report back | Shehab | 2015-01-19 | Mar 24/15: COMPLETE | JAN 12/15:will formulate a plan (or list of outcome measures) w Dr. T to extend lab hours and/or have additional TAs
4 | 2014-09-29 | Shehab to look into organizing a group of students to provide feedback on Clinical Phys Lab changes | Shehab / Cindy /Max | 00-Feb-15 | MAR 24/15: COMPLETE | JAN 12/15: Cindy will organize the focus group
4 | 2014-09-22 | Carmen instructed to send suggestions in resolution of IMGs not having enough time for class readings | Shehab | 2014-10-13 | COMPLETED | An offline discussion on Thursday to speak w IMGs and will report back
7 | 2014-09-22 | VP Academics P/F proposal system will be brought forward to ACC for further discussion | Deans, Directors | Ongoing | COMPLETED | APR 13/15 discussions w curriculum review board are still on-going but will take item off list.
2 | 2014-10-06 | Class reps (or appointed delegate) to either fill out excel chart documenting breaches to 3 day class notes posting rule on moodle | Class Reps, Shehab | 2015-04-13 | COMPLETED | MAR 24/15: the issue has been brought up to faculty and they are more cognicent of the issue (as per JC)
1 | 2014-10-20 | implementation of a focus group and/or produce a set of reasonable procedures for TA-student interactions | Shehab, Cindy | 2015-01-19 | COMPLETED | JAN 12/15: as per Cindy, item completed and a brief report will be presented for next time
1 | 2014-10-27 | invite Michael to come and talk about the issue of dated computers and possibility of up-grading | Shehab | 2015-01-19 | COMPLETED | JAN 12/15: new computers are slowly being installed -- review for next week
2 | 2014-10-27 | e-mail Lawrence (CC: Shehab) about computer crashing issues | Sheryl | 2014-11-10 | COMPLETED | hope to receive a response w/in a month
3 | 2014-11-10 | AV set-up: will remind instructors to end earlier; consider AV set-up early mornings or weekends | Shehab, Melanie | 2014-11-17 | COMPLETED
1 | 2015-05-11 | OAA to provide colored paper with exam review packages for students to record questions/comments to discuss with instructors at Step 3 review | MK | 2015-05-25 | Done | Put in place for the Winter Final 2015 exam reviews
2 | 2014-06-25 | IMG 2017 class received email from Homeopathy instructor which felt threatening, i.e. there would be consequences if they didn't purchase the synthesis text. Nicole Henry will speak with the instructor | N.H. | 2015-07-09 | Done | Instructor apologized, wasn't the intention to threaten or pressure
2 | 2015-07-16 | Melanie to adjust final exam schedule, move asian med exam to Friday, August 14 (has 2 exams scheduled on August 13, class consensus obtained) | M.K. | 2015-07-16 | Done
3 | 2015-07-16 | Year 1 Jan requested acupuncture drop in session prior to final practical exam. Scott to survey class for day/time. Bring back to ADNSA next week for Melanie to secure T.A. | S.D. | 2015-07-23 | Done | Session scheduled for July 27, 5:30pm - 7:30pm
4 | 2015-07-16 | Students asked to test adjustable rolling chairs in the library and to bring feedback to Michael in the LRC and to D. Hall at next week's ADNSA | class reps - all | 2015-07-23 | Done | Students have started to test and providing feedback to Michael in LRC